## V 2.1.0
Update Request
West Bengal Panchayat Asset Management System
Version- 2.1.0
Date-30/09/2024
Sl No. | Type | Issues | Remarks/Action
1 |  | Single Sign-on integation with PMS
2 |  | Dashboard Required
3 | Users- Block Users- | Users spelling correction required
4 | Assets-Enlisted Asset List- | No provition for view all registered assets for all PRI bodies
5 |  | Invalid Zilla Parishad Names- WBCADC, DEV_PRD
6 | Agreement- Make Agreement- New Agreement- | Increament interval for more than 1 year options required.
7 |  | Agreement Item List Block not required in this page
8 |  | Agreement modification cannot be done by maker, if this is rejected by checker or approver. Edit facility required before approval of agreement.
9 | Agreement- Approved Agreement List- Action- | Extention of Agreement provition required, rules as per discussion
10 |  | For all Action options, Asset Name required to be mentioned in that page
11 | Reports- District Wise Report- | As per discussion, reports required in the attached sample format.
12 | Reports-District Wise Report | For GP level detail assets, mention PS name before GP name for proper tagging.
13 | Report | Lisencee wise PRI body wise outstanding payment details report required
14
Remarks-

## V 2.0.0
Update Request
West Bengal Panchayat Asset Management System
Version- 2.0.0
Date-24/06/2024
Sl No. | User Type | Issues | Remarks/Action
1 |  | Users- Users- In Dashboard show ZP/PS/GP name against every user under which that user was registered.
2 |  | Reports- Asset Summary Report- After applying filter, inappropriate data fetching occur, rectification reqiuired.
3 |  | Reports- Disterct wise Tyer wise Total registered Asset Summary required
4 |  | Reports- District wise Tyer wise user count required.
5 |  | DPRDO type user creation should be role free(as Admin) and only have access to the reports section.
Remarks-

## Manual
Issue Register
West Bengal Panchayat Asset Management System
Version- 1.0.0
Date- 04/01/2024
Sl No. | Manual Type | Issues | Remarks/Action
1 | Maker | Clarification of logic, why we create market complex from Master Tab - Market complex, not in asset enlistment | Done
2 | Maker | The purpose for addition of Bank Account details is not mentioned | Done
3 | Maker | Licencee type, 'Individual' and 'Organization' type explanation required | Done
4 | Maker | In report section, Maker user cannot filter Asset Summary Report, User Summary Report & Ledger Summary Report by ZP, PS & GP. Rectify | Done
5 | Checker | Update screenshot, page 16, point 5 (renew), 1st screenshot | Done
6 | Checker | Update screenshot, page 19, point 7.2 (renew), 2nd screenshot | Done
7 | Checker | In report section, Checker user cannot filter Asset Summary Report, User Summary Report & Ledger Summary Report by ZP, PS & GP. Rectify | Done
8 | Approver | Asset tab only contains two options 1. Enlisted Asset 2. Approve Asset Page 6, Point 4.2, rectify content & screenshot | Done
9 | Approver | Agreement tab contains two options 1. Approve Agreement List 2. Approve Agreement Rectify content and screenshot | Done
10 | Approver | Special demand option will not appear for approver profile, rectify content & screenshot | Done
11 | District Admin | In user creation section mention, District admin acn only create Block Admin, District Checker, District Maker & District Approver. | Done
12 | District Admin | Content rectification Page 6, there is no "View All User" button exist in the user page | Done
13 | District Admin | Checker, Maker & Approver responsibilities and relation not mentioned | Done
14 | District Admin | Page 9, Point 5.3, bullet point 3, correction required. | Done
15
Remarks- 1. User with multiple responsibilities manual not recieved.

## V 1.1.0
Issue Register
West Bengal Panchayat Asset Management System
Version- 1.1.0
Date- 04/01/2024
Sl No. | User Type | Issues | Remarks/Action
1 | District Admin | Users - Users filtration against PS & GP for a particular ZP is not working. | Done
2 | District Admin | Report - Summary Report - On click asset count for details 'HTTP 500 Error' occur | Done
3 | District Admin | Report - For a pirticular ZP, PS & GP filter not working, also downloaded excel file either contain null value or dump value in both Asset Summary report & User Summary report | Done
4 | District Admin | Report - For a pirticular ZP, PS & GP filter working, But downloaded excel file either contain null value or dump value in User Summary report | Done
5 | Block Admin | Report - Summary Report - On click asset count for details 'HTTP 500 Error' occur | Done
6 | Block Admin | Report - For a pirticular ZP & PS, GP filter not working, also downloaded excel file either contain null value or dump value in Asset Summary report | Done
7 | Block Admin | Report - For a pirticular ZP & PS, GP filter working, But downloaded excel file either contain null value or dump value in User Summary report | Done
8 | Checker, Maker & Approver - District, Block & GP Level | Above all report issues occur in District Admin & Block Admin login also occur for the said user types | Done
9 | All User | For a download file, file name should be with proper abbreviation. For example: if user download 'Asset Summery Report' then file name should be - Asset Summary Report_<Respective ZP/PS/GP Name>_<Download Date> | Done
10 | All User | District & Block Admin designation need to be selective from some specifice designation | Not Possible
Remarks-

## V 1.0.0
Issue Register
West Bengal Panchayat Asset Management System
Version- 1.0.0
Date- 08/12/2023
|  | By HDFC |  |  | By P&RD on 27.12.2023
Sl No. | Issues | Remarks/Action |  | Test Result | Remarks/Action | Test Result
1 | Designation need to be fixed for ZP Admin & PS Admin | Done |  | Pass | Done | Pass
2 | ZP, PS, GP wise designation filteration. | Done |  | Pass | Done | Pass
3 | User Dashboard- user with multiple permission need to show under job role tab in dashboard against user. | Done |  | Pass | Not done
4 | Bank account of PRI bodies- submission with OTP verification. | Need to Discuss
5 | Id type field verification required for all types of Id | Need to Discuss
6 | New Licensee-If Id and Address matched with already registered licensee, "Same As" button required for copy other data from database. | Only possible for the number. Images need to be uploaded | Done | Pass | Done | Pass
7 | Uploaded image viewing issue for licensee | Done |  | Pass | Done | Pass
8 | Asset list- SWLM change to SLWM | Done |  | Pass | Done | Pass
9 | Both permission (Checker and Maker) not working in the same login | Done |  | Pass | Done | Pass
10 | Add Agreement button available in all pages (Approve Agreement List, Make Agreement, Check Agreement, Approve Agreement ) in super admin login, need to restrict. | Done |  | Pass | Done | Pass
11 | Agreement- Asset type Shop- search field required to find the shop | Done |  | Pass | Done | Pass
12 | Agreement increament time periord- selective dropdown in predefined values- change to monthwise values taken as input | Not Possible at this moment
13 | Payment schedule for previous pending payment- discussion required | discussion required
14 | In Form-5 property details need to add. | Done |  | Pass | Done | Pass
15 | Form-15, header correction required | Done |  | Pass | Done | Pass
16 | In payment dashboard payment status required | Done |  | Pass | Done | Pass
17 | At a time for a district/block only one admin Id can be active. More than one Id activation need to be restricted. | Done |  | Pass | Done | Pass
18 | At the time of licensee regiatration, licensee will receive sms notification after sucessful registration | Need sms content
19 | Agreement- Existing Opening Balance change to Existing Outstanding Balance. | Done |  | Pass | Done | Pass
20 | Demand Details- Penalty, Interest probition for due amount. | Manage with special demand
21 | If any waiver probhition created for all/ indivisuals, notification alert required for those licensee | Sms content required
22 | User Summary Report- Drill down required for details. | Done |  | Pass | Done | Pass
23 | Daily collection- Payment transaction- Collection Purpose change to Collector Name/ Collection Purpose | Done |  | Pass | Done | Pass
24 | If a new form kept save as draft by maker, after reopen that form, already filled fields are not in editabe stage, those field values became freezed. Until submit to next stage all fields need to be in edit mode. | Done |  | Pass | Done | Pass
25 | Make Agreement- Maintenance Charges, Cleaning Charges, Miscellaneaous Charges are calculated against per month, need to mention for those boxes. | Done |  | Pass | Done | Pass
26 | ZP Level Checker- Agreement failed to check by district level checker, error attached. | Done |  |  | Done | Pass
27 | Daily Collection- Payment Transaction- Payment Mode Cash- Form 5 need to be mandatory. Bank Transfer- Reference No. need to be mandatory. | Done |  | Pass | Done | Pass
28 | Summary Report- Check download summary report excel format | Done |  | Pass | Done | Pass
29 | Ongoing agreement terminate error | Done |  |  | Done | Pass
30 | Agreement terminate process should follow Checker Maker Approver concept | Not Possible at this moment
31 | Agreement renual process should follow Checker Maker Approver concept | Not Possible at this moment
32 | Renual of ongoing agreement, agreement renual start date selection should be set after previous agreement last date. Also previous agreement no. and date should automatically fetched from database. | Done |  |  | Not done, only existing agreement no is fetched.
33 | Special demand notice should done by checker only | Done |  | Pass | Done | Pass
34 | Payment against special demand notice is not showing in payment section against agreement | Done |  | Pass | Not done
35 | Listed asset for daily collection not showing in Asset Name list for PS and GP | Done |  | Pass | Not done
Remarks-